# TABLE OF CONTENTS

DOCUMENT 3

COMPLETE DEVELOPMENT ROADMAP

Intelligent Financial Automation and Decision Support System

Month-wise · Week-wise · Day-wise · Developer-wise Execution Plan

Project Duration: 3 Months 10 Days (≈14 Weeks)

Team Size: 2 Developers  |  Availability: 2–3 hrs/day each (4–6 hrs combined)

# HOW TO USE THIS ROADMAP

This roadmap is the master execution plan for the Intelligent Financial Automation and Decision Support System. It is deliberately scoped to a two-person, part-time team working 2–3 hours per developer per day (4–6 hours combined daily effort), across a total window of 3 months and 10 days — approximately 14 working weeks plus a small contingency buffer. Every day in this plan carries exactly one focused task per developer, sized to fit inside a 2–3 hour session. No day assumes parallel multitasking across more than one feature area, and every week ends with a lighter buffer/review day rather than a full workload, so that the plan absorbs slippage without cascading delays.

## Guiding Constraints

- Total timeline: 3 months 10 days (~14 weeks, ~100 working days including buffer).

- 2 developers only — Developer 1 (.NET Backend, React Frontend, Database, Integration) and Developer 2 (Python FastAPI, OCR, AI/ML models).

- 2–3 hours/day per developer; tasks are scoped to be completable within a single focused session.

- Every 7th day of each week is a lighter buffer/review/merge day — never a full-feature day.

- No week loads more than one major feature area per developer to avoid context-switching overhead.

- Testing, integration, and documentation are treated as first-class weeks, not squeezed into feature weeks.

## Team Role Split (used throughout this roadmap)

| Developer | Primary Ownership |
| --- | --- |
| Developer 1 | ASP.NET Core backend (4-layer architecture), React frontend, PostgreSQL database, cross-service integration, testing, documentation |
| Developer 2 | Python FastAPI AI microservice, OCR pipeline, transaction classification, SHAP explainability, anomaly detection, forecasting |

# TIMELINE STRUCTURE OVERVIEW

| Month | Weeks | Focus Area |
| --- | --- | --- |
| Month 1 | Weeks 1–4 | Environment setup, architecture, authentication, frontend scaffold, invoice upload + OCR pipeline |
| Month 2 | Weeks 5–9 | Transaction classification, explainable AI (SHAP), anomaly detection, forecasting (Prophet), dashboard integration |
| Month 3 | Weeks 10–14 | System integration testing, bug fixing & hardening, UAT, documentation & publication draft, final demo prep |
| Final Buffer | Days 99–100+ | Contingency reserve for carried-over fixes and final proofreading |

# SPRINT PLANNING

Development is organised into seven 2-week sprints. Sprint boundaries run independently of calendar-month boundaries so that each sprint stays focused on a single coherent feature set.

| Sprint | Weeks | Sprint Goal |
| --- | --- | --- |
| Sprint 1 | Weeks 1–2 | Environment ready; authentication module complete end-to-end |
| Sprint 2 | Weeks 3–4 | Frontend scaffold + auth UI live; invoice upload & OCR pipeline functional |
| Sprint 3 | Weeks 5–6 | Transaction classification live; SHAP explainability integrated |
| Sprint 4 | Weeks 7–8 | Anomaly detection complete; forecasting (Prophet) module complete |
| Sprint 5 | Weeks 9–10 | Dashboard fully integrated; system integration testing complete |
| Sprint 6 | Weeks 11–12 | System hardened and feature-frozen; UAT complete |
| Sprint 7 | Weeks 13–14 | Documentation & publication draft complete; final demo & submission |

## Weekly Goals & Deliverables (Quick Reference)

| Week | Weekly Goal | Key Deliverable |
| --- | --- | --- |
| 1 | Dev environments & architecture ready | Scaffolded repos, DB schema draft, OCR POC |
| 2 | Authentication module complete | JWT auth (register/login) end-to-end |
| 3 | Frontend scaffold + auth UI complete | React app with working login/register flow |
| 4 | Invoice upload + OCR functional | Invoice → OCR → transaction pipeline (Month 1 done) |
| 5 | Transaction classification live | Auto-categorised transactions with confidence score |
| 6 | Explainable AI (SHAP) integrated | Per-transaction explanation panel in UI |
| 7 | Anomaly detection complete | Flagged anomalies with reasons in UI |
| 8 | Forecasting module complete | Prophet-based cash-flow forecast chart |
| 9 | Full feature set integrated | Complete dashboard (Month 2 done) |
| 10 | Integration testing complete | Defect log, performance & security baseline |
| 11 | System hardened & feature-frozen | Zero critical bugs; UAT-ready build |
| 12 | UAT complete | UAT summary report + satisfaction scores |
| 13 | Documentation & publication draft complete | Full report + paper draft + slide deck v1 |
| 14 | Final demo & submission | v1.0 tagged release, submitted project (Month 3 done) |

# MONTH 1 — FOUNDATION: SETUP, AUTH, FRONTEND, INVOICE & OCR (WEEKS 1–4)

## Week 1 — Environment Setup & Architecture Planning

| Day | Developer 1 Tasks | Developer 2 Tasks | Expected Output | Git Commit(s) | Deliverable |
| --- | --- | --- | --- | --- | --- |
| Day 1 | Set up GitHub repo, branch strategy (main/develop/feature); install VS2022 + .NET 8 SDK | Install Python 3.11, create venv, install FastAPI + Uvicorn | Both dev environments ready | chore: initial repo setup | Repo initialized with README |
| Day 2 | Draft ER diagram; finalize core DB schema (Users, Invoices, Transactions) | Research OCR libraries; verify PaddleOCR install | Draft schema + OCR environment verified | docs: initial db schema draft | schema.md committed |
| Day 3 | Create ASP.NET Core solution with 4-layer projects (Domain/Application/Infrastructure/API) | Set up FastAPI project skeleton with folder structure | Both skeletons compile and run | feat: scaffold backend solution | Running hello-world endpoints on both sides |
| Day 4 | Configure PostgreSQL connection string; install EF Core packages | Set up requirements.txt; verify OpenCV + pdf2image install | DB connection tested; AI libs installed | chore: configure ef core + postgres | Verified DB connectivity |
| Day 5 | Create Domain entities (User, Invoice, Transaction) + DbContext skeleton | Build standalone OCR proof-of-concept script (image → text) | Entities defined; OCR POC successful | feat: add domain entities | Working OCR proof-of-concept script |
| Day 6 | Create initial EF Core migration and apply to DB | Document initial AI architecture and module plan | DB tables created; AI architecture drafted | feat: initial ef core migration | Migrated DB + AI architecture note |
| Day 7 (Buffer) | Weekly review; align on internal API contract with Dev2 | Weekly review; align on internal API contract with Dev1 | Agreed API contract draft | docs: week 1 sync notes | Milestone: Dev environment & architecture ready |

## Week 2 — Authentication Module

| Day | Developer 1 Tasks | Developer 2 Tasks | Expected Output | Git Commit(s) | Deliverable |
| --- | --- | --- | --- | --- | --- |
| Day 1 | Implement User entity service, password hashing, POST /auth/register | Set up FastAPI OCR router skeleton (routes only) | Register API functional (Postman tested) | feat: user registration api | POST /auth/register working |
| Day 2 | Implement JWT login endpoint and token generation | Implement pdf2image conversion utility function | Login returns JWT; utility tested | feat: jwt login endpoint | POST /auth/login working |
| Day 3 | Add JWT authentication middleware + role-based authorization attributes | Implement OpenCV pre-processing (deskew, denoise, contrast) | Protected endpoints require valid JWT; preprocessing tested | feat: jwt auth middleware | Auth-protected test endpoint |
| Day 4 | Write xUnit tests for auth services | Integrate PaddleOCR detection + recognition into pipeline function | Auth unit tests passing; OCR returns raw text | test: auth unit tests | Test report + raw-text OCR output |
| Day 5 | Add global exception handling middleware + standard error format | Test OCR pipeline on 5 sample invoices; log accuracy issues | Consistent error responses; OCR accuracy notes | feat: global exception handler | Error-handling middleware + OCR test log |
| Day 6 | Add Serilog logging setup (console + file sink) | Parse OCR output into structured JSON stub (vendor/date/amount) | Logs written to file; OCR returns structured stub | feat: serilog integration | Logging config + OCR JSON stub |
| Day 7 (Buffer) | Code review; merge auth branch to develop | Code review; support auth merge testing | Auth module merged and stable | merge: auth module to develop | Milestone: Authentication module complete |

## Week 3 — Frontend Scaffold, Auth UI & DB Finalization

| Day | Developer 1 Tasks | Developer 2 Tasks | Expected Output | Git Commit(s) | Deliverable |
| --- | --- | --- | --- | --- | --- |
| Day 1 | Scaffold React app (Vite) with Router and folder structure | Build POST /internal/ocr/extract endpoint wired to pipeline | React app runs; OCR endpoint returns JSON | feat: react app scaffold | Running dev server + working OCR API |
| Day 2 | Build Login page UI + authService.js (Axios) | Write pytest unit tests for OCR utilities | Login UI functional against backend | feat: login page ui | Login page connected to API |
| Day 3 | Build Register page UI; implement AuthContext for token storage | Add structured logging to FastAPI requests | Full register→login flow working | feat: register page + auth context | End-to-end auth flow in UI |
| Day 4 | Implement PrivateRoute wrapper in React Router | Draft Dockerfile for FastAPI service | Unauthenticated users redirected; Docker image builds | feat: protected routes | Route guarding + buildable Docker image |
| Day 5 | Finalize remaining DB tables (Predictions, Anomalies, Logs, Reports) + migration | Research/plan transaction dataset sources (Kaggle, synthetic) | Full schema migrated; dataset plan documented | feat: complete db schema | Full DB schema live |
| Day 6 | Build Dashboard page shell (empty widgets) + navigation layout | Prepare initial sample transaction dataset (~500-1000 rows) | Dashboard shell navigable; sample dataset ready | feat: dashboard shell | Dataset v0.1 (CSV) |
| Day 7 (Buffer) | Integration check: frontend auth ↔ backend; weekly review | Support integration check from AI-service side | Auth + navigation stable end-to-end | chore: week 3 integration fixes | Milestone: Frontend scaffold + Auth UI complete |

## Week 4 — Invoice Upload & OCR Integration (Month 1 Close)

| Day | Developer 1 Tasks | Developer 2 Tasks | Expected Output | Git Commit(s) | Deliverable |
| --- | --- | --- | --- | --- | --- |
| Day 1 | Build Invoice entity, InvoiceService, POST /invoices/upload (multipart) | Clean & label sample transaction dataset (category tagging) | Upload endpoint stores file + creates Invoice record | feat: invoice upload api | Working upload endpoint |
| Day 2 | Build React Invoice Upload page (file picker) + Axios call | Write data cleaning script (dedupe, normalize text) | Upload UI functional; cleaned dataset v0.2 | feat: invoice upload ui | Upload UI connected to API |
| Day 3 | Implement HttpClient service in .NET calling FastAPI OCR endpoint | Begin embedding generation script (all-MiniLM-L6-v2) | .NET successfully calls FastAPI OCR; embeddings generated | feat: fastapi client integration | Cross-service call working |
| Day 4 | Persist OCR-extracted fields into Invoice + create Transaction records | Continue embedding pipeline; store embeddings (parquet/numpy) | Uploaded invoice auto-populates transaction; embeddings stored | feat: persist ocr results | End-to-end invoice → transaction flow |
| Day 5 | Build Invoice list/detail page in React showing OCR results | Train baseline XGBoost classifier on embeddings (v0.1) | UI shows extracted invoice data; baseline model trained | feat: invoice detail ui | Baseline classifier (unevaluated) |
| Day 6 | Add invoice status indicators (Pending/Processed/Failed) | Evaluate baseline model (accuracy/F1 on validation split) | Status UI working; evaluation report v0.1 | feat: invoice status ui | Model evaluation report |
| Day 7 (Buffer) | Month 1 demo: invoice upload + OCR flow; retro | Month 1 demo support; retro | Stable Month 1 build | chore: month 1 wrap-up | Milestone: Invoice upload + OCR pipeline functional |

# MONTH 2 — INTELLIGENCE LAYER: CLASSIFICATION, XAI, ANOMALY, FORECASTING (WEEKS 5–9)

## Week 5 — Transaction Classification Integration

| Day | Developer 1 Tasks | Developer 2 Tasks | Expected Output | Git Commit(s) | Deliverable |
| --- | --- | --- | --- | --- | --- |
| Day 1 | Design classification API contract (request/response schema) | Hyperparameter tuning round 1 on XGBoost classifier | Agreed API schema; improved model metrics | docs: classification api contract | API contract document |
| Day 2 | Build ClassificationClient wrapper in .NET | Build POST /internal/classify/transaction endpoint | .NET can call classify endpoint (basic response) | feat: classification client + endpoint | Working classify endpoint |
| Day 3 | Wire classification into transaction-creation flow; persist Category/Confidence | Save trained model (save_model.py) + build model_loader.py | New transactions auto-classified end-to-end | feat: auto-classify on create | End-to-end classification flow |
| Day 4 | Update React transaction list to show Category + confidence badge | Write predict.py inference script + unit tests | Category visible in UI; inference tested | feat: category display ui | Category shown in transaction table |
| Day 5 | Add manual category override (edit category in UI + API) | Benchmark classification latency; optimize batch inference | Users can correct categories; latency under target | feat: manual category override | Override feature + latency benchmark |
| Day 6 | Write integration tests for classification flow | Expand dataset; retrain model v0.2 | Integration tests passing; improved model v0.2 | test: classification integration tests | Test report + model v0.2 |
| Day 7 (Buffer) | Weekly review; merge classification branch | Weekly review; support merge testing | Classification module stable | merge: classification module | Milestone: Transaction classification live |

## Week 6 — Explainable AI (SHAP) Integration

| Day | Developer 1 Tasks | Developer 2 Tasks | Expected Output | Git Commit(s) | Deliverable |
| --- | --- | --- | --- | --- | --- |
| Day 1 | Design SHAP explanation JSON schema; plan DB column | Set up SHAP TreeExplainer on trained XGBoost model | Schema agreed; SHAP values computed offline | docs: shap schema design | Sample SHAP output |
| Day 2 | Add ShapExplanationJson column + migration | Extend classify endpoint to return SHAP values | DB ready to store explanations; endpoint returns SHAP JSON | feat: shap db column + endpoint | Working XAI-enabled endpoint |
| Day 3 | Wire explanation storage into classification flow | Format SHAP output into human-readable top-features list | Explanation persisted per transaction | feat: persist shap explanation | Explanation data stored per transaction |
| Day 4 | Build React explanation panel/tooltip component | Unit test SHAP formatting logic | UI shows 'why this category' panel | feat: explanation panel ui | Explanation UI component |
| Day 5 | Add visual feature-contribution bars (Chart.js) to explanation panel | Optimize SHAP computation performance (TreeSHAP settings) | Visual explanation bars rendering; faster SHAP calls | feat: shap visualization | Visual SHAP bars in UI |
| Day 6 | Write tests for explanation panel rendering | Document SHAP integration approach (for publication notes) | Tests passing; documentation drafted | test: explanation panel tests | XAI documentation draft |
| Day 7 (Buffer) | Weekly review; code review & merge XAI branch | Weekly review; support merge testing | XAI module stable | merge: xai module | Milestone: Explainable AI (SHAP) integrated |

## Week 7 — Anomaly Detection (Isolation Forest)

| Day | Developer 1 Tasks | Developer 2 Tasks | Expected Output | Git Commit(s) | Deliverable |
| --- | --- | --- | --- | --- | --- |
| Day 1 | Design Anomalies API usage (list/review endpoints) | Feature-engineer transaction data (amount, vendor freq, time gaps) | API design agreed; feature set defined | docs: anomaly feature design | Feature engineering notes |
| Day 2 | Build GET /api/v1/anomalies endpoint (list/filter) | Train Isolation Forest model on engineered features | Endpoint returns data; model trained | feat: anomalies list api + train model | Trained anomaly model v0.1 |
| Day 3 | Build trigger/stub to invoke anomaly scan from API | Build POST /internal/anomaly/scan endpoint | .NET can trigger scan; endpoint returns anomaly scores | feat: anomaly scan trigger + endpoint | Working anomaly scan flow |
| Day 4 | Persist anomaly results (score, reason, severity) into DB | Generate human-readable reason strings for flagged anomalies | Anomalies stored with reasons | feat: persist anomalies | Anomaly records with reasons |
| Day 5 | Build React Anomalies page (list with severity badges) | Validate detection against injected synthetic anomalies | Anomalies UI functional; validation report ready | feat: anomalies ui | Anomalies page live |
| Day 6 | Add 'Mark as Reviewed' action (API + UI) | Tune Isolation Forest contamination parameter | Review workflow working; tuned model v0.2 | feat: anomaly review action | Review workflow + tuned model |
| Day 7 (Buffer) | Weekly review; merge anomaly detection branch | Weekly review; support merge testing | Anomaly detection module stable | merge: anomaly detection module | Milestone: Anomaly detection complete |

## Week 8 — Prediction Module (Prophet)

| Day | Developer 1 Tasks | Developer 2 Tasks | Expected Output | Git Commit(s) | Deliverable |
| --- | --- | --- | --- | --- | --- |
| Day 1 | Design Predictions API contract for forecast data | Prepare aggregated historical transaction time-series | Contract agreed; time-series dataset ready | docs: prediction api contract | Aggregated dataset for forecasting |
| Day 2 | Build GET /api/v1/predictions endpoint (by metric type) | Build Prophet training script (CashFlow/Revenue/Expense) | Stub endpoint; Prophet model trained on sample data | feat: predictions api + train prophet | Offline forecast output |
| Day 3 | Build .NET integration client for forecast endpoint | Build POST /internal/prediction/forecast endpoint | End-to-end forecast call working | feat: prediction integration | Working forecast API |
| Day 4 | Persist forecast results into Predictions table | Add confidence interval (lower/upper bound) to Prophet output | Forecasts stored with bounds | feat: persist predictions | Forecast records in DB |
| Day 5 | Scaffold GET /dashboard/summary endpoint aggregating KPIs | Backtest Prophet model (rolling-origin evaluation) | Summary API returns KPIs; backtest report ready | feat: dashboard summary api | KPI summary endpoint + backtest report |
| Day 6 | Build Chart.js cash-flow trend chart with forecast band | Optimize Prophet retraining schedule/frequency logic | Trend chart rendering with forecast overlay | feat: cashflow chart | Working forecast chart |
| Day 7 (Buffer) | Weekly review; merge prediction branch | Weekly review; support merge testing | Prediction module stable | merge: prediction module | Milestone: Forecasting module complete |

## Week 9 — Dashboard Integration & Polish (Month 2 Close)

| Day | Developer 1 Tasks | Developer 2 Tasks | Expected Output | Git Commit(s) | Deliverable |
| --- | --- | --- | --- | --- | --- |
| Day 1 | Build category-wise spend pie/bar chart component | Package trained models (classifier, isolation forest, prophet) into models_store with versioning | Spend chart live; models versioned & documented | feat: category spend chart + model versioning | Chart component + versioned models folder |
| Day 2 | Build anomaly summary widget on dashboard | Write model loading integration tests (model_loader.py) | Anomaly widget shows counts/severity | feat: anomaly summary widget | Dashboard anomaly widget |
| Day 3 | Assemble full Dashboard layout (all widgets) + responsive styling | Optimize FastAPI startup (model preloading) for latency | Cohesive dashboard page; faster cold-start | feat: dashboard layout | Complete dashboard page v1 |
| Day 4 | Add date-range filters to dashboard queries | Add caching layer for repeated inference requests | Filters working; caching reduces repeat latency | feat: dashboard filters | Filterable dashboard |
| Day 5 | Cross-browser/responsive UI testing & fixes | Run full AI pipeline smoke test (OCR→classify→anomaly→predict) | UI polished; pipeline smoke test passes | fix: ui responsiveness | Smoke test report |
| Day 6 | Write Jest component tests for dashboard widgets | Document AI service API (Swagger/OpenAPI via FastAPI) | Tests passing; AI API docs auto-generated | test: dashboard component tests | FastAPI Swagger docs live |
| Day 7 (Buffer) | Month 2 demo: full-feature walkthrough; retro | Month 2 demo support; retro | All core features integrated | chore: month 2 wrap-up | Milestone: Full feature set integrated |

# MONTH 3 — QUALITY & DELIVERY: TESTING, UAT, DOCUMENTATION, DEMO (WEEKS 10–14)

## Week 10 — System Integration Testing

| Day | Developer 1 Tasks | Developer 2 Tasks | Expected Output | Git Commit(s) | Deliverable |
| --- | --- | --- | --- | --- | --- |
| Day 1 | Write end-to-end integration test plan (auth→upload→OCR→classify→anomaly→predict) | Support integration test planning from AI-service side | Test plan document; initial bugs logged | docs: integration test plan | Test plan + bug list |
| Day 2 | Execute integration tests across modules; log defects | Fix AI-service-side defects from Day 1 findings | Defect list triaged; fixes in progress | fix: integration bugs batch 1 | Updated bug tracker |
| Day 3 | Fix backend/frontend-side defects from integration testing | Re-run model evaluation after any data/label fixes | Open defect count reduced; stable model metrics | fix: backend/frontend bugs batch 1 | Defect count reduced ~50% |
| Day 4 | Performance/load testing of ASP.NET API (Postman/k6) | Latency benchmarking of FastAPI endpoints under load | Performance baseline report for both services | test: performance benchmarks | Performance report |
| Day 5 | Address backend performance bottlenecks (indexing, queries) | Address AI-service latency bottlenecks (batching, async) | Improved response times | perf: optimize db queries + ai latency | Updated benchmark numbers |
| Day 6 | Security review: JWT expiry, role checks, input validation audit | Security review of FastAPI endpoints (validation, upload safety) | Security checklist completed; issues logged | security: audit fixes batch 1 | Security audit report |
| Day 7 (Buffer) | Weekly review; remaining defect triage | Weekly review; remaining defect triage | System stable for UAT prep | chore: week 10 wrap-up | Milestone: Integration testing complete |

## Week 11 — Bug Fixing & Hardening

| Day | Developer 1 Tasks | Developer 2 Tasks | Expected Output | Git Commit(s) | Deliverable |
| --- | --- | --- | --- | --- | --- |
| Day 1 | Fix remaining high-priority backend/frontend bugs | Fix remaining high-priority AI-service bugs | Critical bugs resolved | fix: critical bugs batch 2 | Critical bug count = 0 |
| Day 2 | Improve error messages & UI validation feedback | Improve error handling/logging in FastAPI | Better UX for failures on both sides | feat: improved error handling | Consistent error UX |
| Day 3 | Add loading states/skeletons for async UI operations | Add retry/timeout handling for internal API calls | Smoother UX; resilient service calls | feat: loading states + retry policy | Improved reliability |
| Day 4 | Finalize role-based access control edge cases | Re-validate anomaly & prediction models on refreshed data | RBAC fully verified; models re-validated | fix: rbac edge cases | RBAC test report |
| Day 5 | Regression testing pass across all frontend/backend modules | Regression testing of AI endpoints (contract tests) | No regressions found, or all fixed | test: regression pass | Regression test report |
| Day 6 | Prepare pilot UAT test accounts/sample data | Prepare AI-service demo dataset (clean, representative) | UAT environment ready | chore: uat prep | UAT-ready environment |
| Day 7 (Buffer) | Weekly review; freeze feature branch for UAT | Weekly review; freeze feature branch for UAT | Feature-complete, stable build | chore: feature freeze | Milestone: System hardened & feature-frozen |

## Week 12 — User Acceptance Testing (UAT)

| Day | Developer 1 Tasks | Developer 2 Tasks | Expected Output | Git Commit(s) | Deliverable |
| --- | --- | --- | --- | --- | --- |
| Day 1 | Onboard pilot users; walk through core flows | Monitor AI-service logs during pilot sessions | Pilot session 1 completed | docs: uat session 1 notes | UAT feedback batch 1 |
| Day 2 | Collect & triage UAT feedback (bugs vs. enhancements) | Triage AI-related feedback (explanation clarity, accuracy) | Feedback backlog created | docs: uat feedback backlog | Prioritized feedback list |
| Day 3 | Fix top UAT-reported backend/frontend issues | Fix top UAT-reported AI/explanation issues | Key issues resolved | fix: uat issues batch 1 | Updated build |
| Day 4 | Conduct pilot session 2 with fixes applied | Support session 2; capture satisfaction survey responses | Session 2 completed; survey data collected | docs: uat session 2 notes | UAT satisfaction scores |
| Day 5 | Analyze UAT survey results; document usability findings | Analyze AI-specific feedback (trust, anomaly usefulness) | UAT summary report drafted | docs: uat summary report | UAT summary report |
| Day 6 | Implement final quick-win UX improvements from UAT | Implement final quick-win AI/explanation improvements | Polished final build | feat: final uat improvements | Near-final build |
| Day 7 (Buffer) | Weekly review | Weekly review | UAT complete, build stable | chore: week 12 wrap-up | Milestone: UAT complete |

## Week 13 — Documentation & Publication Draft

| Day | Developer 1 Tasks | Developer 2 Tasks | Expected Output | Git Commit(s) | Deliverable |
| --- | --- | --- | --- | --- | --- |
| Day 1 | Write/update system architecture & API documentation | Write AI methodology section for publication draft | Draft docs in progress | docs: architecture documentation | Architecture doc draft |
| Day 2 | Write user manual / setup guide (README, install steps) | Prepare evaluation metrics tables/figures for publication | Setup guide complete; metrics tables ready | docs: setup guide | README + metrics tables |
| Day 3 | Compile project report sections (architecture, testing, results) | Draft publication paper introduction, related work, methodology | Report sections compiled; paper ~40% complete | docs: project report compilation | Report draft v1 |
| Day 4 | Prepare final database & API reference appendix | Draft publication paper results & discussion sections | Appendices complete; paper ~70% complete | docs: api reference appendix | Full API reference |
| Day 5 | Review & proofread full project documentation | Review & proofread publication paper draft | Documentation review complete | docs: proofreading pass | Reviewed documentation |
| Day 6 | Prepare presentation slides (architecture, features, demo flow) | Prepare presentation slides (AI pipeline, results, SHAP examples) | Draft slide deck ready | docs: presentation slides draft | Slide deck v1 |
| Day 7 (Buffer) | Weekly review; finalize publication submission checklist | Weekly review; finalize publication submission checklist | Publication draft near-final | chore: week 13 wrap-up | Milestone: Documentation & publication draft complete |

## Week 14 — Final Demo & Presentation Preparation

| Day | Developer 1 Tasks | Developer 2 Tasks | Expected Output | Git Commit(s) | Deliverable |
| --- | --- | --- | --- | --- | --- |
| Day 1 | Rehearse full live demo flow end-to-end | Prepare AI-specific demo talking points (explainability walkthrough) | Demo script finalized | docs: demo script | Demo script + flow |
| Day 2 | Fix last-minute bugs found during demo rehearsal | Fix last-minute AI-service bugs found during rehearsal | Stable demo build | fix: pre-demo bugs | Demo-ready build |
| Day 3 | Finalize presentation slides & speaker notes | Finalize presentation slides & speaker notes (AI sections) | Slide deck finalized | docs: final slides | Final slide deck |
| Day 4 | Conduct mock presentation/demo run-through | Participate in mock run-through; refine AI Q&A prep | Mock-run feedback incorporated | docs: mock demo feedback | Refined presentation |
| Day 5 | Final documentation formatting & submission packaging | Final publication draft formatting & submission packaging | All submission artefacts finalized | chore: final packaging | Submission-ready package |
| Day 6 (Buffer) | Contingency buffer — address any outstanding risk items | Contingency buffer — address any outstanding risk items | Zero open blockers | chore: final buffer fixes | Fully stable final build |
| Day 7 | Final review; tag release v1.0; project submission | Final review; tag release v1.0; project submission | Project submitted | release: v1.0 final submission | Milestone: Project complete & submitted |

## Final Buffer Days (Days 99–100+, Contingency Reserve)

A small contingency reserve beyond the 14-week core plan, aligned to the full 3-month-10-day duration, absorbing any residual slippage without affecting the submission deadline.

| Day | Developer 1 Tasks | Developer 2 Tasks | Expected Output | Git Commit(s) | Deliverable |
| --- | --- | --- | --- | --- | --- |
| Buffer Day 1 | Address any carried-over defects or reviewer feedback | Address any carried-over AI/model issues | Fully clean build with zero open issues | fix: final contingency fixes | Contingency fixes applied |
| Buffer Day 2 | Final proofreading of all submitted documents | Final proofreading of publication draft & AI documentation | All documents submission-ready | docs: final proofreading pass | Final submission package |

# CODE REVIEW SCHEDULE

- Every feature branch is opened as a Pull Request (PR) against 'develop' before merging — no direct commits to 'develop' or 'main'.

- Given the 2-person team, both developers review each other's PRs; a PR is not self-merged.

- Lightweight daily review: each developer skims the other's latest commit(s) at the start of their next session (5–10 minutes) to stay in sync.

- Formal weekly review: Day 7 of every week is reserved for a full PR review + merge session for that week's feature branch(es).

- Sprint-end review: at the close of each 2-week sprint, both developers jointly review the merged 'develop' branch before considering the sprint closed.

# TESTING, INTEGRATION, BUFFER & PUBLICATION WEEKS

| Category | Weeks | Purpose |
| --- | --- | --- |
| Continuous Unit Testing | Every week (ongoing) | Unit tests written alongside each feature (xUnit, pytest, Jest) |
| Integration Weeks | Week 9, Week 10 | Dashboard integration (Week 9) and full system integration testing (Week 10) |
| Dedicated Testing Weeks | Week 10, Week 11 | Integration testing, performance/security testing, regression testing, bug hardening |
| UAT Week | Week 12 | Pilot user sessions, feedback collection, satisfaction survey |
| Buffer Days | Day 7 of every week + Week 14 Day 6 + Final Buffer Days | Absorb slippage; no new feature work scheduled |
| Publication Weeks | Week 13 (primary), Week 9 Day 1 (metrics prep) | Drafting and finalising the publication paper alongside project documentation |
| Demo Preparation | Week 14, Days 1–4 | Rehearsing and hardening the live demo flow |
| Presentation Preparation | Week 13 Days 6–7, Week 14 Days 3–4 | Building and refining the slide deck and speaker notes |

# GITHUB WORKFLOW

## Branch Strategy

- main — always production-ready; only sprint-end merges from 'develop' land here, tagged with a version (e.g., v0.1, v0.2 ... v1.0).

- develop — integration branch; all completed weekly feature branches merge here after review.

- feature/<short-name> — one branch per feature (e.g., feature/invoice-upload, feature/shap-explainer); branched from 'develop', merged back via PR.

- fix/<short-name> — for bug fixes identified during testing/UAT weeks.

- docs/<short-name> — for documentation-only changes (Week 13 onward).

## Commit Message Convention

Conventional Commits style is used throughout this roadmap for traceability: feat: (new feature), fix: (bug fix), docs: (documentation), test: (tests), chore: (tooling/config), perf: (performance), security: (security-related change), merge: (branch merge), release: (version tag).

## Pull Request Checklist (before requesting review)

- Branch is up to date with 'develop' (rebased/merged).

- Code builds/runs locally without errors.

- Relevant unit tests written and passing.

- No secrets/credentials committed (.env files git-ignored).

- PR description lists what changed and how to test it.

# DAILY / WEEKLY / MONTHLY CHECKLISTS

## Daily Checklist (per developer, every session)

- Pull latest changes from 'develop' before starting.

- Review today's single scheduled task on the roadmap/task board.

- Implement the task within the 2–3 hour session window.

- Commit with a Conventional Commit message before ending the session.

- Update task status on the shared board (Backlog → In Progress → Review → Done).

- Post a 1–2 line async update to the other developer (what was done, any blockers).

## Weekly Checklist (every Day 7)

- Review the week's goal against what was actually delivered.

- Run the full test suite (backend, AI service, frontend) before merging.

- Review and merge the week's feature branch(es) into 'develop'.

- Update the shared task board and roadmap document with any deviations.

- Note any risks or slippage in the risk register (see Risk Management).

- Confirm next week's tasks are still realistic given current progress.

## Monthly Checklist (end of Month 1, 2, 3)

- Run a full regression test across all integrated modules.

- Merge 'develop' into 'main' and tag a version milestone (v0.1, v0.2, v1.0).

- Conduct a short retrospective: what worked, what to adjust for the next month.

- Update the risk register and re-baseline the remaining roadmap if needed.

- Demo the month's working build end-to-end to confirm milestone completion.

# RISK MANAGEMENT

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Limited daily hours (2–3 hrs) cause task overrun | Medium | High | Tasks are pre-scoped to fit one session; Day 7 buffer absorbs overflow before it compounds |
| OCR accuracy lower than expected on varied invoice formats | Medium | Medium | Early standalone OCR POC (Week 1) surfaces issues before dependent features are built |
| Classification/anomaly model accuracy insufficient | Medium | Medium | Iterative retraining scheduled (v0.1 → v0.2) with dedicated evaluation days |
| Cross-service integration delays (.NET ↔ FastAPI) | Medium | High | API contracts are agreed and documented one day before implementation each time |
| Scope creep beyond the defined feature set | Low | High | Feature list is fixed per the architecture blueprint; new ideas go to Future Enhancements, not the current sprint |
| Developer unavailability (illness, exams, etc.) | Medium | Medium | Weekly buffer days + monthly re-baselining absorb short absences; final buffer days act as last-resort reserve |
| Publication draft quality suffers under time pressure | Medium | Medium | Publication writing starts early (Week 9 metrics prep) rather than being confined to Week 13 alone |
| Dataset scarcity for training/evaluation | Medium | Medium | Synthetic + public dataset blend planned from Week 3; documented in Document 2 (AI Development Guide) |

# CONSOLIDATED MILESTONES

| Milestone | Target Week | Signals |
| --- | --- | --- |
| Dev environment & architecture ready | Week 1 | Both stacks scaffolded and running |
| Authentication module complete | Week 2 | JWT register/login working end-to-end |
| Frontend scaffold + auth UI complete | Week 3 | React auth flow live against backend |
| Invoice upload + OCR pipeline functional (Month 1 done) | Week 4 | Uploaded invoice auto-creates transactions |
| Transaction classification live | Week 5 | Transactions auto-categorised with confidence score |
| Explainable AI (SHAP) integrated | Week 6 | Per-transaction explanation visible in UI |
| Anomaly detection complete | Week 7 | Flagged anomalies with reasons visible in UI |
| Forecasting module complete | Week 8 | Cash-flow forecast chart with confidence band |
| Full feature set integrated (Month 2 done) | Week 9 | Complete dashboard combining all modules |
| Integration testing complete | Week 10 | Defect log + performance/security baseline documented |
| System hardened & feature-frozen | Week 11 | Zero critical bugs; build frozen for UAT |
| UAT complete | Week 12 | UAT summary report + satisfaction scores collected |
| Documentation & publication draft complete | Week 13 | Full report + paper draft + slide deck v1 ready |
| Project complete & submitted (Month 3 done) | Week 14 | v1.0 tagged, final demo delivered, project submitted |